## Sheet1
Flashee
Project Estimation Report #1
| Date | 2021-11-01
| Moderator | Álvar San Martin
| Estimator 1 | Ângelo Paiva
| Estimator 2 | Burak Tinman
| Estimator 3 | Jan Frank
| Estimator 4 | Pedro Henriques
WBS
Stage | Task | Subtask | Effort | Assumptions
2.1. Requirements Specification | 2.1.1 Software Requirement Specification
|  | 2.1.1.1 Analysis | 7 | 16 requirements, 5 use cases, 2-3 mockups
|  | 2.1.1.2 Writing | 5
|  | 2.1.1.3 Review | 5 | Using Inspection method
2.1.2 Risk Plan
|  | 2.1.2.1 Analysis | 3 | 5-10 risks
|  | 2.1.2.2 Writing | 3
|  | 2.1.2.3 Review | 2 | Using Deskcheck method
2.1.3 Acceptance Test Plan
|  | 2.1.3.1 Analysis | 6 | same number as requirements
|  | 2.1.3.2 Writing | 3
|  | 2.1.3.3 Review | 2 | Using Deskcheck method
2.1.4 Milestone M2.1 Report
|  | 2.1.4.1 Analysis | 1
|  | 2.1.4.2 Writing | 2
|  | 2.1.4.3 Review | 1 | Using Deskcheck method
2.2 Software Development | 2.2.1 Software Architecture & Design
|  | 2.2.1.1 Analysis | 8
|  | 2.2.1.2 Designing | 7 | Architecture and class diagram
|  | 2.2.1.3 Review | 4 | Using Deskcheck method
| 2.2.2 Source Code |  |  | Times include testing and reviews (Deskcheck)
|  | 2.2.2.1 Create Cards | 3 | Unit testing
|  | 2.2.2.2 Modify existing cards | 2 | Unit testing
|  | 2.2.2.3 Topic Sorting | 2 | Unit testing
|  | 2.2.2.4 Import-Export User Decks | 5 | Integration Testing
|  | 2.2.2.5 Practice Mode | 4 | Unit testing
|  | 2.2.2.6 Search for certain card | 2 | Unit testing
|  | 2.2.2.7 User Stats | 3 | Unit testing
|  | 2.2.2.8 Annotations | 2 | Unit testing
|  | 2.2.2.9 Tag via difficulty | 2 | Unit testing
|  | 2.2.2.10 Card Design | 4 | Acceptance testing
|  | 2.2.2.11 UX Design | 7 | Acceptance testing
|  | 2.2.2.12 Design the leaderbords | 2 | Acceptance testing
|  | 2.2.2.13 Animations | 2 | Acceptance testing
|  | 2.2.2.14 Easy to view/access tags | 2 | Acceptance testing
|  | 2.2.2.15 Clearly visible difficulty of cards | 2 | Acceptance testing
|  | 2.2.2.16 Easy visible practice time | 2 | Acceptance testing
2.2.3 User Documentation
|  | 2.2.3.1 Analysis | 3 | Small manual for users to get started with the app
|  | 2.2.3.2 Writing | 5
|  | 2.2.3.3 Review | 2 | Using Deskcheck method
2.2.4 Milestone M2.2 Report
|  | 2.2.4.1 Analysis | 2
|  | 2.2.4.2 Writing | 2
|  | 2.2.4.3 Review | 1 | Using Deskcheck method
2.3. Software Acceptance | 2.3.1 Acceptance Test Report
|  | 2.3.1.1 Analysis | 2
|  | 2.3.1.2 Writing | 4
|  | 2.3.1.3 Review | 2 | Using Deskcheck method
2.3.2 Quality Assesment Report
|  | 2.3.2.1 Check quality controls (metrics) | 3 | We estimate it based on the number of metrics we are using to measure the quality of the project.
|  | 2.3.2.2 Writing | 3
|  | 2.3.2.3 Review | 2 | Using Deskcheck method
2.3.3 Milestone M2.3 Report
|  | 2.3.3.1 Analysis | 1
|  | 2.3.3.2 Writing | 2
|  | 2.3.3.3 Review | 1 | Using Deskcheck method
|  | Total | 140