## BaselinePlan
Stages:
1. Project Preparation
2. Project Execution
3. Project Closeup
Phases: |  |  |  |  | Milestones:
1.1 - Project Setup & Software Concept |  |  |  |  | M1.1 - Scope Review
1.2 - Project Planning | [8 empty] | M1.2 - Plan Review
2.1 - Requirements Specification | [10 empty] | M2.1 - Software Requirements Review
2.2 - Software Development | [14 empty] | M2.2 - Design Review
2.3 - Software Acceptance | [15 empty] | M2.3 - Acceptance Review
3.1 - Project Closeup | [16 empty] | M3.1 - Closeup
| Week | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
| Date (for Lab3) | 2021-10-12 | 2021-10-19 | 2021-10-26 | 2021-11-02 | 2021-11-09 | 2021-11-16 | 2021-11-30 | 2021-12-07 | 2021-12-14 | 2021-12-21 | 2021-12-28 | 2022-01-04 | 2022-01-11 | 2022-01-18 | 2022-01-25
|  | 2021-10-12 | 2021-10-19 | 2021-10-26 | 2021-11-02 | 2021-11-09 | 2021-11-16 | 2021-11-30 | 2021-12-07 | 2021-12-14 | 2021-12-21 | 2021-12-28 | 2022-01-04 | 2022-01-11 | 2022-01-18 | 2022-01-25
|  | opc. | - optional, the team members decide if they want to work during Christmas
|  | * | - extra class