## Gantt
GPS-ISEC Flashee Earned Value Analysis |  |  | Budgeted Cost of Work (BCW) |  |  |  |  | Actual Cost of Work (ACW) |  |  |  | Earned Value Analysis | Calendar (weeks)
| Baselined schedule |  | Planned start | Planned complete | Start from previous start | Planned duration (weeks) | Estimated effort (hours) | Actual start | Actual complete | Actual effort (hours) | Actual value (hours) |  | 2021-12-07 | 2021-12-14 | 2021-12-21 | 2021-12-28 | 2022-01-04 | 2022-01-11 | 2022-01-18 | 2022-01-25
[13 empty] | 07-12-2021 | 14-12-2021 | 21-12-2021 | 28-12-2021 | 04-01-2022 | 11-01-2022 | 18-01-2022 | 25-01-2022 | 00-01-1900 | 00-01-1900 | 00-01-1900 | 00-01-1900 | 00-01-1900 | 00-01-1900
| Baseline 1 | 2021-12-07 | 2021-12-07 | 2022-01-25 |  | 7 | 140 |  |  |  |  | Budget at Completion (BAC) | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140
[12 empty] | Planned Value (PV) | 0 | 19 | 40 | 62 | 82 | 103 | 124 | 140
[12 empty] | Earned Value (EV) | 0 | 19 | 40 | 47 | 54 | 112 | 119 | 135
WBS | Live values |  | 2021-12-07 | 2022-01-25 |  | 7 | 140 | 2021-12-07 | 2021-12-14 | 118 | 128 | Actual Cost (AC) | 0 | 15 | 32 | 39 | 46 | 95 | 102 | 118
Stage | Task | Subtask | [9 empty] | Notes | 2021-12-07: Actual work expended (Mark with X when task completed)
2.1. Requirements Specification | 2.1.1 Software Requirement Specification | 2.1.1.1 Analysis | 2021-12-07 | 2021-12-14 |  | 1 | 7 | 2021-12-07 | 2021-12-14 | 7 | 7 | 11 requirements, 8 use cases, ? mockups |  | 7 | x | x | x | x | x | x | x | x | x | x | x | x
2.1. Requirements Specification | 2.1.1 Software Requirement Specification | 2.1.1.2 Write | 2021-12-07 | 2021-12-14 | 0 | 1 | 6 | 2021-12-07 | 2021-12-14 | 5 | 6 |  |  | 5 | x | x | x | x | x | x | x | x | x | x | x | x
2.1. Requirements Specification | 2.1.1 Software Requirement Specification | 2.1.1.3 Review | 2021-12-14 | 2021-12-21 | 1 | 1 | 4 | 2021-12-14 | 2021-12-21 | 2 | 4 | Using Inspection method |  |  | 2 | x | x | x | x | x | x | x | x | x | x | x
2.1. Requirements Specification | 2.1.2 Risk Plan | 2.1.2.1 Analysis | 2021-12-07 | 2021-12-14 | -1 | 1 | 3 | 2021-12-07 | 2021-12-14 | 2 | 3 | 5-10 risks |  | 2 | x | x | x | x | x | x | x | x | x | x | x | x
2.1. Requirements Specification | 2.1.2 Risk Plan | 2.1.2.2 Write | 2021-12-07 | 2021-12-14 | 0 | 1 | 3 | 2021-12-07 | 2021-12-14 | 1 | 3 | [9 empty] | x | x | x | x | x | x | bar: 2021-12-14 to 2022-01-25
2.1. Requirements Specification | 2.1.2 Risk Plan | 2.1.2.3 Review | 2021-12-14 | 2021-12-21 | 1 | 1 | 2 | 2021-12-14 | 2021-12-21 | 1 | 2 | Using Deskcheck method | [8 empty] | x | x | x | x | x | x | bar: 2021-12-21 to 2022-01-25
2.1. Requirements Specification | 2.1.3 Acceptance Test Plan | 2.1.3.1 Analysis | 2021-12-14 | 2021-12-21 | 0 | 1 | 3 | 2021-12-14 | 2021-12-21 | 3 | 3 | same number as requirements |  |  | 3 | x | x | x | x | x | x | x | x | x | x | x
2.1. Requirements Specification | 2.1.3 Acceptance Test Plan | 2.1.3.2 Write | 2021-12-14 | 2021-12-21 | 0 | 1 | 3 | 2021-12-14 | 2021-12-21 | 2 | 3 |  |  |  | 2 | x | x | x | x | x | x | x | x | x | x | x
2.1. Requirements Specification | 2.1.3 Acceptance Test Plan | 2.1.3.3 Review | 2021-12-21 | 2021-12-28 | 1 | 1 | 2 | 2021-12-21 | 2021-12-28 | 2 | 2 | Using Deskcheck method |  |  |  | 2 | x | x | x | x | x | x | x | x | x | x
2.1. Requirements Specification | 2.1.4 Milestone M2.1 Report | 2.1.4.1 Analysis | 2021-12-14 | 2021-12-21 | -1 | 1 | 1 | 2021-12-14 | 2021-12-21 | 1 | 1 | [9 empty] | x | x | x | x | x | x | bar: 2021-12-21 to 2022-01-25
2.1. Requirements Specification | 2.1.4 Milestone M2.1 Report | 2.1.4.2 Write | 2021-12-14 | 2021-12-21 | 0 | 1 | 1 | 2021-12-14 | 2021-12-21 | 1 | 1 | [9 empty] | x | x | x | x | x | x | bar: 2021-12-21 to 2022-01-25
2.1. Requirements Specification | 2.1.4 Milestone M2.1 Report | 2.1.4.3 Review | 2021-12-21 | 2021-12-28 | 1 | 1 | 1 | 2021-12-21 | 2021-12-28 | 1 | 1 | Using Deskcheck method | [8 empty] | x | x | x | x | x | x | bar: 2021-12-28 to 2022-01-25
2.2. SW Development | 2.2.1 Software Architecture & Design | 2.2.1.1 Analysis | 2021-12-14 | 2021-12-21 | -1 | 1 | 3 | 2021-12-14 | 2021-12-21 | 3 | 3 |  |  |  | 3 | x | x | x | x | x | x | x | x | x | x | x
2.2. SW Development | 2.2.1 Software Architecture & Design | 2.2.1.2 Design | 2021-12-14 | 2021-12-21 | 0 | 1 | 4 | 2021-12-14 | 2021-12-21 | 4 | 4 | Architecture and class diagram |  |  | 4 | x | x | x | x | x | x | x | x | x | x | x
2.2. SW Development | 2.2.1 Software Architecture & Design | 2.2.1.3 Review | 2021-12-21 | 2021-12-28 | 1 | 1 | 4 | 2021-12-21 | 2021-12-28 | 4 | 4 | Using Deskcheck method |  |  |  | 4 | x | x | x | x | x | x | x | x | x | x
2.2. SW Development | 2.2.2 Source Code | 2.2.2.1 Create Cards | 2021-12-21 | 2021-12-28 | 0 | 1 | 4 | 2021-12-28 | 2022-01-04 | 4 | 4 | Unit testing | 2022-01-04: 4; 2022-01-11: x; 2022-01-18: x; 2022-01-25: x | x | x | x | x | x | x
2.2. SW Development | 2.2.2 Source Code | 2.2.2.2 Modify existing cards | 2021-12-21 | 2021-12-28 | 0 | 1 | 3 | 2021-12-28 | 2022-01-04 | 3 | 3 | Unit testing | 2022-01-04: 3; 2022-01-11: x; 2022-01-18: x; 2022-01-25: x | x | x | x | x | x | x
2.2. SW Development | 2.2.2 Source Code | 2.2.2.3 Topic Sorting | 2021-12-21 | 2021-12-28 | 0 | 1 | 2 | 2022-01-04 | 2022-01-11 | 2 | 2 | Unit testing | 2022-01-11: 2; 2022-01-18: x; 2022-01-25: x | x | x | x | x | x | x
2.2. SW Development | 2.2.2 Source Code | 2.2.2.4 Import-Export User Decks | 2021-12-21 | 2021-12-28 | 0 | 1 | 6 | 2022-01-04 | 2022-01-11 | 4 | 6 | Integration Testing | 2022-01-11: 4; 2022-01-18: x; 2022-01-25: x | x | x | x | x | x | x
2.2. SW Development | 2.2.2 Source Code | 2.2.2.5 Practice Mode | 2021-12-28 | 2022-01-04 | 1 | 1 | 5 | 2022-01-04 | 2022-01-11 | 4 | 5 | Unit testing | 2022-01-11: 4; 2022-01-18: x; 2022-01-25: x | x | x | x | x | x | x
2.2. SW Development | 2.2.2 Source Code | 2.2.2.6 Search for certain card | 2021-12-28 | 2022-01-04 | 0 | 1 | 2 | 2022-01-04 | 2022-01-11 | 2 | 2 | Unit testing | 2022-01-11: 2; 2022-01-18: x; 2022-01-25: x | x | x | x | x | x | x
2.2. SW Development | 2.2.2 Source Code | 2.2.2.7 User Stats | 2021-12-28 | 2022-01-04 | 0 | 1 | 4 | 2022-01-04 | 2022-01-11 | 4 | 4 | Unit testing | 2022-01-11: 4; 2022-01-18: x; 2022-01-25: x | x | x | x | x | x | x
2.2. SW Development | 2.2.2 Source Code | 2.2.2.8 Annotations | 2021-12-28 | 2022-01-04 | 0 | 1 | 2 | 2022-01-04 | 2022-01-11 | 2 | 2 | Unit testing | 2022-01-11: 2; 2022-01-18: x; 2022-01-25: x | x | x | x | x | x | x
2.2. SW Development | 2.2.2 Source Code | 2.2.2.9 Tag via difficulty | 2021-12-28 | 2022-01-04 | 0 | 1 | 3 | 2022-01-04 | 2022-01-11 | 3 | 3 | Unit testing | 2022-01-11: 3; 2022-01-18: x; 2022-01-25: x | x | x | x | x | x | x
2.2. SW Development | 2.2.2 Source Code | 2.2.2.10 Card Design | 2021-12-28 | 2022-01-04 | 0 | 1 | 4 | 2022-01-04 | 2022-01-11 | 4 | 4 | Acceptance testing | 2022-01-11: 4; 2022-01-18: x; 2022-01-25: x | x | x | x | x | x | x
2.2. SW Development | 2.2.2 Source Code | 2.2.2.11 UX Design | 2022-01-04 | 2022-01-18 | 1 | 2 | 7 | 2022-01-04 | 2022-01-11 | 7 | 7 | Acceptance testing | 2022-01-11: 7; 2022-01-18: x; 2022-01-25: x | x | x | x | x | x | x
2.2. SW Development | 2.2.2 Source Code | 2.2.2.12 Design the leaderbords | 2022-01-04 | 2022-01-11 | 0 | 1 | 3 | 2022-01-04 | 0 | 0 | 0 | Acceptance testing | 2022-01-11: 0
2.2. SW Development | 2.2.2 Source Code | 2.2.2.13 Animations | 2022-01-04 | 2022-01-11 | 0 | 1 | 3 | 2022-01-04 | 2022-01-11 | 3 | 3 | Acceptance testing | 2022-01-11: 3; 2022-01-18: x; 2022-01-25: x | x | x | x | x | x | x
2.2. SW Development | 2.2.2 Source Code | 2.2.2.14 Easy to view/access tags | 2022-01-04 | 2022-01-11 | 0 | 1 | 2 | 2022-01-04 | 2022-01-11 | 2 | 2 | Acceptance testing | 2022-01-11: 2; 2022-01-18: x; 2022-01-25: x | x | x | x | x | x | x
2.2. SW Development | 2.2.2 Source Code | 2.2.2.15 Clearly visible difficulty of cards | 2022-01-04 | 2022-01-11 | 0 | 1 | 3 | 2022-01-04 | 2022-01-11 | 1 | 3 | Acceptance testing | [8 empty] | x | x | x | x | x | x | bar: 2022-01-11 to 2022-01-25
2.2. SW Development | 2.2.2 Source Code | 2.2.2.16 Easy visible practice time | 2022-01-04 | 2022-01-11 | 0 | 1 | 3 | 2022-01-04 | 2022-01-11 | 1 | 3 | Acceptance testing | [8 empty] | x | x | x | x | x | x | bar: 2022-01-11 to 2022-01-25
2.2. SW Development | 2.2.3 User Documentation | 2.2.3.1 Analysis | 2022-01-04 | 2022-01-11 | 0 | 1 | 3 | 2022-01-04 | 2022-01-11 | 3 | 3 | Small manual for users to get started with the app | 2022-01-11: 3; 2022-01-18: x; 2022-01-25: x | x | x | x | x | x | x
2.2. SW Development | 2.2.3 User Documentation | 2.2.3.2 Write | 2022-01-11 | 2022-01-18 | 1 | 1 | 5 | 2022-01-04 | 2022-01-11 | 3 | 5 |  | 2022-01-11: 3; 2022-01-18: x; 2022-01-25: x | x | x | x | x | x | x
2.2. SW Development | 2.2.3 User Documentation | 2.2.3.3 Review | 2022-01-11 | 2022-01-18 | 0 | 1 | 2 | 2022-01-11 | 0 | 0 | 0 | Using Deskcheck method | 2022-01-18: 0
2.2. SW Development | 2.2.4 Milestone M2.2 Report | 2.2.4.1 Analysis | 2022-01-04 | 2022-01-11 | -1 | 1 | 2 | 2022-01-04 | 2022-01-11 | 2 | 2 |  | 2022-01-11: 2; 2022-01-18: x; 2022-01-25: x | x | x | x | x | x | x
2.2. SW Development | 2.2.4 Milestone M2.2 Report | 2.2.4.2 Write | 2022-01-04 | 2022-01-11 | 0 | 1 | 2 | 2022-01-04 | 2022-01-11 | 2 | 2 |  | 2022-01-11: 2; 2022-01-18: x; 2022-01-25: x | x | x | x | x | x | x
2.2. SW Development | 2.2.4 Milestone M2.2 Report | 2.2.4.3 Review | 2022-01-11 | 2022-01-18 | 1 | 1 | 1 | 2022-01-11 | 2022-01-18 | 1 | 1 | Using Deskcheck method | [8 empty] | x | x | x | x | x | x | bar: 2022-01-18 to 2022-01-25
2.3. SW Acceptance | 2.3.1 Acceptance Test Report | 2.3.1.1 Analysis | 2022-01-11 | 2022-01-18 | 0 | 1 | 2 | 2022-01-11 | 2022-01-18 | 2 | 2 |  | 2022-01-18: 2; 2022-01-25: x | x | x | x | x | x | x
2.3. SW Acceptance | 2.3.1 Acceptance Test Report | 2.3.1.2 Write | 2022-01-11 | 2022-01-18 | 0 | 1 | 4 | 2022-01-11 | 2022-01-18 | 4 | 4 |  | 2022-01-18: 4; 2022-01-25: x | x | x | x | x | x | x
2.3. SW Acceptance | 2.3.1 Acceptance Test Report | 2.3.1.3 Review | 2022-01-18 | 2022-01-25 | 1 | 1 | 2 | 2022-01-18 | 0 | 2 | 0 | Using Deskcheck method | 2022-01-25: 2
2.3. SW Acceptance | 2.3.2 Quality Assessment Report | 2.3.2.1 Check quality control (metrics) | 2022-01-18 | 2022-01-25 | 0 | 1 | 3 | 2022-01-18 | 2022-01-25 | 3 | 3 | We estimate it based on the number of metrics we are using to measure the quality of the project. | 2022-01-25: 3 | x | x | x | x | x | x
2.3. SW Acceptance | 2.3.2 Quality Assessment Report | 2.3.2.2 Write | 2022-01-18 | 2022-01-25 | 0 | 1 | 3 | 2022-01-18 | 2022-01-25 | 3 | 3 |  | 2022-01-25: 3 | x | x | x | x | x | x
2.3. SW Acceptance | 2.3.2 Quality Assessment Report | 2.3.2.3 Review | 2022-01-18 | 2022-01-25 | 0 | 1 | 3 | 2022-01-18 | 0 | 3 | 0 | Using Deskcheck method | 2022-01-25: 3
2.3. SW Acceptance | 2.3.3 Milestone M2.3 Report | 2.3.3.1 Analysis | 2022-01-18 | 2022-01-25 | 0 | 1 | 1 | 2022-01-18 | 2022-01-25 | 1 | 1 | [9 empty] | x | x | x | x | x | x | bar: 2022-01-25
2.3. SW Acceptance | 2.3.3 Milestone M2.3 Report | 2.3.3.2 Write | 2022-01-18 | 2022-01-25 | 0 | 1 | 2 | 2022-01-18 | 2022-01-25 | 2 | 2 |  | 2022-01-25: 2 | x | x | x | x | x | x
2.3. SW Acceptance | 2.3.3 Milestone M2.3 Report | 2.3.3.3 Review | 2022-01-18 | 2022-01-25 | 0 | 1 | 2 | 2022-01-18 | 0 | 2 | 0 | Using Deskcheck method | 2022-01-25: 2
[8 empty] | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
Formulas:
Budgeted Cost of Work (BCW) = IF(OR(ISBLANK(N2),ISBLANK([GPS-ISEC Flashee Earned Value Analysis])),"",OFFSET(N2,0,F10+MATCH([Budgeted Cost of Work (BCW), row above],N2:AA2,0)-1))
Actual Cost of Work (ACW) = IFERROR(INDEX(N2:AA2,1,(MATCH(1,IF(ISNUMBER([Calendar (weeks)]:AA9),1,0),0))-1),0)

## Tables
Stage
2.1. Requirements Specification
2.2. SW Development
2.3. SW Acceptance