## Team Log
Week | From | To | Tasks Done | Effort
1 | 2020-10-13 | 2020-10-19 | MSTeams preparation, V&S draft and GitHub repo. | 20
2 | 2020-10-20 | 2020-10-26 | Create Jira board, review V&S and submit to approval, prepare milestone 1.1 for review. | 15.2856
3 | 2020-10-27 | 2020-11-02 | SDP draft (1, 2, 3.1 and 4), WBS, Planning poker, Project Estimation Report | 21.183
4 | 2020-11-03 | 2020-11-09 | Last week action items, first QAP draft | 15.366
5 | 2020-11-10 | 2020-11-16 | Action items of week 4, finishing SDP, QAP, WBS, QAR and EVA | 18.476
6 | 2020-11-17 | 2020-11-23 | Action items of last week, submitting all the documents mention before for approval (SDP, QAP, WBS, QAR and EVA), writing and submiting the milestone report for approval. | 15.268
7 | 2020-11-24 | 2020-11-30 | Reviewing SDP, WBS, QAP, EVA and approve; Working on SRS, ATP, RP, prepare Meeting | 17.637
8 | 2020-12-01 | 2020-12-07 | SRS Inspection and follow-up meeting | 20.379
9 | 2020-12-08 | 2020-12-14 | SRS inspections | 15.829
10 | 2020-12-15 | 2020-12-21 | MR2.1, ATP | 3.14
11 | 2020-12-22 | 2020-12-28 | General development | 13.3
12 | 2020-12-29 | 2021-01-04 | General development | 40.8
13 | 2021-01-05 | 2021-01-11 | Testing | 18.25
14 | 2021-01-12 | 2021-01-18 | Deployment, pots-mortem and publishing | 26.32
|  |  | Total | 261.2336
Formulas:
To = [From]+6
From = [From, row above]+7

## Alvar
Week | From | To | Tasks Done | Effort
1 | 2020-10-13 | 2020-10-19 | Project discusion, D1.1.1 V&S document elaboration | 4
2 | 2020-10-20 | 2020-10-26 | D1.1.1 review and correction | 1.45
3 | 2020-10-27 | 2020-11-02 | D1.2.1 point 2 and 3.1 | 4.53
4 | 2020-11-03 | 2020-11-09 | Corrections of D1.2.1 and point 7 of D2.1.2 | 4.15
5 | 2020-11-10 | 2020-11-16 | QAP point 5, meeting minutes week 5 | 3.15
6 | 2020-11-17 | 2020-11-23 | Review of the previous documents, creation of the milestone report | 2.5
7 | 2020-11-24 | 2020-12-07 | 2.1.1SRS, mockups and use cases | 4.2
8 | 2020-12-08 | 2020-12-14 | SRS Inspection and preparing of documents | 3.1
9 | 2020-12-15 | 2020-12-21 | SRS fixes, risk plan, git setup | 4.28
10 | 2020-12-22 | 2020-12-28 | On vacation | 0
11 | 2020-12-29 | 2021-01-04 | Development of the base, database init | 13.3
12 | 2021-01-05 | 2021-01-11 | Development of components | 2.45
13 | 2021-01-12 | 2021-01-18 | Development of components | 5.3 | ,
14 | 2021-01-19 | 2021-01-25 | Presentation, post-mortem | 4.53
|  |  | Total | 56.94
Formulas:
To = [From]+6
From = [From, row above]+7

## Ângelo
Week | From | To | Tasks Done | Effort
1 | 2020-10-13 | 2020-10-19 | V&S draft, project discussion, add team description, embelish dashboard, create Git repository, fix some issues with project files (versioning now is working properly), prefill the minute for the meeting | 4
2 | 2020-10-20 | 2020-10-26 | Finish V&S, review and submit to approval, create Jira board, review Milestone report | 3.89 | 233min
3 | 2020-10-27 | 2020-11-02 | SDP sections 2 and 3.1, prepare agenda for next meeting, planning poker, WBS, project estimation report | 4.3 | 258min
4 | 2020-11-03 | 2020-11-09 | QAP (sections 1, 2, 3 and 6), last week's action items | 2.75 | 165min
5 | 2020-11-10 | 2020-11-16 | EVA, QAR, finish QAP and SDP | 4.17 | 250min
6 | 2020-11-17 | 2020-11-23 | Finishing previous documents, submitting for approval | 3.67 | 220min
7 | 2020-11-24 | 2020-12-07 | Preparing SRS, team and self assessment, ATR | 3.94 | 236min
8 | 2020-12-08 | 2020-12-14 | SRS Inspection and follow-up meeting | 5.08 | 305min
9 | 2020-12-15 | 2020-12-21 | MR2.1, ATP, prefill the minute for the meeting | 2.27 | 136min
10 | 2020-12-22 | 2020-12-28 | Unable to work because of school assignments | 0
11 | 2020-12-29 | 2021-01-04 | Unable to work because of school assignments | 0
12 | 2021-01-05 | 2021-01-11 | Front-end, help with tests | 12.22 | 733min
13 | 2021-01-12 | 2021-01-18 | QAR and support document, help with other parts | 3.96 | 223min
14 | 2021-01-19 | 2021-01-25 | Presentation, post-mortem | 4.1 | 246min
|  |  | Total | 54.35 | Weekly objective: 240min | Average: | 3.8821
Formulas:
To = [From]+6
From = [From, row above]+7

## Burak
Week | From | To | Tasks Done | Effort
1 | 2020-10-13 | 2020-10-19 | Sharepoint, Dashboard and V&S draft preparation. | 4
2 | 2020-10-20 | 2020-10-26 | Finishing V&S, create JIRA Board, preparing Agenda for Tuesday, organizing Team assignments (approving documents) | 3.72
3 | 2020-10-27 | 2021-11-01 | Handling action items for week 2, organizing team assignments, working on SDP section 4, Planning poker | 3.82
4 | 2020-11-03 | 2020-11-09 | Handling action items for week 3, working on QAP section 4 | 2.9
5 | 2020-11-10 | 2020-11-16 | Handling action items for week 4, fixing SDP, WBS, QAP, QAR, adding EVA to dashboard | 3.61
6 | 2020-11-17 | 2020-11-23 | Handling action items for week 5, fixing WBS, writing on the Milestone report, reviewing documents | 3.79
7 | 2020-11-24 | 2020-12-07 | Reviewing SDP; WBS; QAP; EVA; and approve; Working on SRS, ATP, RP, prepare Meeting | 4.2
8 | 2020-12-08 | 2020-12-14 | SRS Inspection, prostprocessing Inspection, SAD prep | 3.75
9 | 2020-12-15 | 2020-12-21 | Writing SAD, MR2.1, Approving documents | 3.62
10 | 2020-12-22 | 2020-12-28 | Worked on feedback on SRS, RP, ATP and MR | 3.14
11 | 2020-12-29 | 2021-01-04 | Illness /
12 | 2021-01-05 | 2021-01-11 | Implementation of Import/Export, Deletion of Card, Milestone report | 7.3
13 | 2021-01-12 | 2021-01-18 | Working on QAR, ATR, MR, fixing bugs in code | 5.34
14 | 2021-01-19 | 2021-01-25 | Finishing post mortem analysis, wrap up project | 5.76
|  |  | Total | 54.95
Formulas:
To = [From]+6
From = [From, row above]+7

## Jan
Week | From | To | Tasks Done | Effort
1 | 2020-10-13 | 2020-10-19 | Vision & Scope draft preparation. | 4
2 | 2020-10-20 | 2020-10-26 | Preparation of Milestone 1.1 Report, planning regular weekly schedule, building Jira dashboard and To-do list. | 3.1126
3 | 2020-10-27 | 2020-11-02 | Added SDP issues to Jira board, wrote introduction for the Software Development Plan, played planning poker and helping with the Project Estimation Report #1. | 4.513
4 | 2020-11-03 | 2020-11-09 | Review of week 3's action items, wrote section 2 of the Quality Assurance Plan. | 3.016
5 | 2020-11-10 | 2020-11-16 | Review and fixing of last week's action items, preparation of the EVA. | 3.916
6 | 2020-11-17 | 2020-11-23 | Fixing previous documents and submitting them for approval | 2.548
7 | 2020-11-24 | 2020-12-07 | SRS, team and self assessment (didn't go through for some reason) | 3.127
8 | 2020-12-08 | 2020-12-14 | Final preparations for the SRS and its Inspection, start of M2.1 Report | 5.619
9 | 2020-12-15 | 2020-12-21 | SRS follow-up meeting, M2.1 Report, SAD, finishing ATP, adjusting EVA | 3.329
10 | 2020-12-22 | 2020-12-28 | Christmas week + university assignments | 0
11 | 2020-12-29 | 2021-01-04 | Unable to work due to university assignments | 0
12 | 2021-01-05 | 2021-01-11 | Back-end features, some front-end | 14.62
13 | 2021-01-12 | 2021-01-18 | Bug-fixing | 2.73
14 | 2021-01-19 | 2021-01-25 | Presentation + post-mortem | 4.71 | 3.9458
|  |  | Total | 55.2406
Formulas:
To = [From]+6
From = [From, row above]+7

## Pedro
Week | From | To | Tasks Done | Effort
1 | 2020-10-13 | 2020-10-19 | Project discussion & adding new ideas to Vision & Scope | 4
2 | 2020-10-20 | 2020-10-26 | Prepared Milestone 1.1 report, planned weekly schedule, set up for Jira dashboard, weekly member to-do list. | 3.113
3 | 2020-10-27 | 2020-11-02 | Sorting starting plan, setup inital WBS draft, poker planning, Software Development plan setup, aiding with Project Estimation Report WBS update | 4.02
4 | 2020-11-03 | 2020-11-09 | Aiding with Project Estimation Report, graph of WBS, project discussion, Section 3 of the Quality Assurance Plan | 2.55
5 | 2020-11-10 | 2020-11-16 | Initial project discussion, QAR | 3.63
6 | 2020-11-17 | 2020-11-23 | Rectifying mistakes from previous documents, discussing the Milestone report with colleagues. | 2.76
7 | 2020-11-24 | 2020-12-07 | Worked on the Functional Requirements within the SRS | 2.17
8 | 2020-12-08 | 2020-12-14 | SRS Inspection Meeting | 2.83
9 | 2020-12-15 | 2020-12-21 | Worked on Software Architecture & Design's class diagrams | 2.33
10 | 2020-12-22 | 2020-12-28 | Unable to work due to Christmas week | 0
11 | 2020-12-29 | 2021-01-04 | Unable to work due to other class assignments | 0
12 | 2021-01-05 | 2021-01-11 | Reviewed certain parts of the code, tested app on Safari, wrote User Manual. | 4.21
13 | 2021-01-12 | 2021-01-18 | Was unable to work much due to three different class assignments for around the same days. | 0.92
14 | 2021-01-19 | 2021-01-25 | Worked on the final presentation. | 7.22
|  |  | Total | 39.753
Formulas:
To = [From]+6
From = [From, row above]+7

## Sum
Week | Budget | Average | Burak | Ângelo | Alvar | Jan | Pedro
1 | 4 | 4 | 4 | 4 | 4 | 4 | 4
2 | 8 | 7.0571 | 7.72 | 7.89 | 5.45 | 7.1126 | 7.113 | 15.276
3 | 12 | 11.2937 | 11.54 | 12.19 | 9.98 | 11.6256 | 11.133
4 | 16 | 14.3669 | 14.44 | 14.94 | 14.13 | 14.6416 | 13.683
5 | 20 | 18.0621 | 18.05 | 19.11 | 17.28 | 18.5576 | 17.313
6 | 24 | 21.1157 | 21.84 | 22.78 | 19.78 | 21.1056 | 20.073
7 | 28 | 24.6431 | 26.04 | 26.72 | 23.98 | 24.2326 | 22.243
8 | 32 | 28.7189 | 29.79 | 31.8 | 27.08 | 29.8516 | 25.073
9 | 36 | 31.8847 | 33.41 | 34.07 | 31.36 | 33.1806 | 27.403
10 | 40 | 32.5127 | 36.55 | 34.07 | 31.36 | 33.1806 | 27.403
11 | 44 | 35.1727 | 36.55 | 34.07 | 44.66 | 33.1806 | 27.403
12 | 48 | 43.3327 | 43.85 | 46.29 | 47.11 | 47.8006 | 31.613
13 | 52 | 46.9827 | 49.19 | 50.25 | 52.41 | 50.5306 | 32.533
14 | 56 | 52.2467 | 54.95 | 54.35 | 56.94 | 55.2406 | 39.753